## Sheet1
Memoria Studios
Template | https://themeforest.net/item/yani-clean-and-minimalist-photography-wordpress-theme/23686692
Page |  | Details | Design | Coding | Copywriting
1 | Home Page | Upcoming scheduled trips or plans, promos, gallery, social proof, our clients | 70%
2 | Our Services | 1 Main Page containing all of our services
3 | Wedding Photo | Pre, Actual | Done
4 | Wedding Video | Pre-Production, Animation, Actual | Done
5 | Maternal Photo | Preg/Natal, Newborn | Done
6 | Corporate Photo | Events, Promotional, Stock
7 | Our Work (or Gallery) | 1 Main Page containing all of our works
8 | Past Weddings
9 | Past Maternal
10 | Past Community Projects
11 | Contact/Feedback | Review first and awards then contact info
12 | Booking Page
13 | About Us
14 | Legal (PDPA release) | 1 page containing Privacy policy and T&C
15 | Site map
Optional | Pop up - ongoing promo (KIV)
Timeline |  |  | Design | Coding | Copywriting
Sunday | 1 Nov 2020 |  | At the moment done 4 pages | OTOT
Monday | 2 Nov 2020 |  |  | OTOT |  | Week 12
Tuesday | 3 Nov 2020 |  |  | OTOT |  | Week 12
Wednesday | 4 Nov 2020 |  | OTOT | OTOT | OTOT | Week 12
Thursday | 5 Nov 2020 |  | First draft of all pages | OTOT | Finalize all packages | Week 12
Friday | 6 Nov 2020 |  | Amendment of first draft | Done at least 5 - 8 pages | OTOT | Week 12
Saturday | 7 Nov 2020 |  | Finalize design of all pages | OTOT | OTOT | Week 12
Sunday | 8 Nov 2020 |  | FOCUS ON FYP INTERIM REPORTS YO! TOMORROW IS SUBMISSION DAY
Monday | 9 Nov 2020 |  | FOCUS ON FYP INTERIM REPORTS YO! IT IS SUBMISSION DAY |  |  | Week 13
Tuesday | 10 Nov 2020 | Google Analytics & Creative Brief |  | OTOT | OTOT | Week 13
Wednesday | 11 Nov 2020 | Google Analytics & Checking |  | Finalize coding of all pages | Finalize all copywriting | Week 13
Thursday | 12 Nov 2020 | Checking |  |  |  | Week 13
Friday | 13 Nov 2020 | Checking & Submission |  |  |  | Week 13